## Sprint 1
Day | Ideal Progress | Actual Remaining SP
1 | 21 | 21 | Planning day: Sprint goals defined.
2 | 18 | 18 | Stakeholder interviews delayed (2 SP not burned).
3 | 15 | 16 | Wireframes & dashboards designed (2.5 SP burned).
4 | 12 | 14 | Modular architecture finalized (2.5 SP burned).
5 | 9 | 12 | UI components refined (3 SP burned).
6 | 6 | 8 | Feedback incorporated (3 SP burned).
7 | 3 | 4 | Final wireframes approved (3.5 SP burned).
8 | 0 | 2
Day | Ideal Progress | Actual Remaining SP
1 | 30 | 30
2 | 25.7 | 28
3 | 21.4 | 26
4 | 17.1 | 22
5 | 12.8 | 16
6 | 8.5 | 4
7 | 4.2 | 7
8 | 0 | 3.9
Day | Ideal Progress | Actual Remaining SP
1 | 18 | 18
2 | 15.75 | 16
3 | 13.5 | 14
4 | 11.25 | 12
5 | 9 | 9
6 | 6.75 | 6
7 | 4.5 | 3
8 | 2.25 | 0

## Sprint 2
Day | Ideal Burndown | Actual Burndown
0 | 34 | 34
1 | 29.75 | 28.9
2 | 25.5 | 25.5
3 | 21.25 | 20.4
4 | 17 | 17
5 | 12.75 | 11.9
6 | 8.5 | 8.5
7 | 4.25 | 3.4
8 | 0 | 0

## Sprint 3
Day | Ideal Burndown | Actual Burndown
0 | 18 | 18
1 | 15.75 | 15.3
2 | 13.5 | 13.5
3 | 11.25 | 10.8
4 | 9 | 9
5 | 6.75 | 6.3
6 | 4.5 | 4.5
7 | 2.25 | 1.8
8 | 0 | 0