## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | LearnBridge
| Project Manager: | Khadija Imran
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five week project.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent weekly on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a week. This is estimated on a weekly basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a week. This is estimated on a weekly basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Week | This is the number of hours spent on a given task for the week.
| Starting Hours | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Actual Effort (Hours) | 96 | 31 | -50 | -131 | -212 | -304
Ideal Effort (Hours) | 96 | 76.8 | 57.6 | 38.4 | 19.2 | 0
Tasks | Starting Hours | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Total
Task 1 | 12 | 11 | 11 | 11 | 11 | 22 | 66
Task 2 | 12 | 10 | 10 | 10 | 10 | 10 | 50
Task 3 | 12 | 4 | 10 | 10 | 10 | 10 | 44
Task 4 | 12 | 8 | 10 | 10 | 10 | 10 | 48
Task 5 | 12 | 8 | 10 | 10 | 10 | 10 | 48
Task 6 | 12 | 8 | 10 | 10 | 10 | 10 | 48
Task 7 | 12 | 8 | 10 | 10 | 10 | 10 | 48
Task 8 | 12 | 8 | 10 | 10 | 10 | 10 | 48